# MINUTES OF MEETING

Meeting Title: Planning for Engineers’ Day Fest

Date: 9th September 2026

Time: 3:00 PM – 4:30 PM

Venue/Platform: Seminar Hall, DYPiu University

Facilitator: Prof. Labhini Rahangdale

Recorder: Sahil Singh

# 1. Attendance

- Present: Prof. Labhini Rahangdale, Mr. Rajesh Patil, Student Coordinators (Rohan, Priya, Sahil)

- Absent: None

# 2. Agenda Items

- Theme finalization for Engineers’ Day Fest

- Event schedule planning

- Budget allocation and sponsorships

- Volunteer responsibilities

- Publicity and promotion strategy

# 3. Discussion Summary

- Theme Finalization: Decided on “Innovation for a Sustainable Future” as the central theme.

## Event Schedule:

  - Guest Lecture by industry expert at 10:00 AM

  - Project Exhibition from 11:30 AM – 2:00 PM

  - Technical Quiz at 2:30 PM

  - Cultural Program at 5:00 PM

- Budget & Sponsorships: Estimated budget ₹50,000. Sponsorship requests to be sent to local tech companies.

- Volunteers: 20 student volunteers to be divided into logistics, hospitality, and technical support teams.

- Publicity: Posters, social media campaigns, and announcements in classrooms to begin from 12th September.

# 4. Decisions Made

- Theme confirmed: “Innovation for a Sustainable Future”

- Event schedule finalized as above

- Budget approved at ₹50,000

- Sponsorship committee formed (Rohan & Priya)

- Publicity to start on 12th September

# 5. Action Items

| ## Task | ## Responsible Person | ## Deadline |
| --- | --- | --- |
| Contact guest speaker | Prof. Labhini Rahangdale | 10th Sept 2026 |
| Prepare sponsorship letters | Rohan & Priya | 12th Sept 2026 |
| Design posters & social media posts | Sahil | 11th Sept 2026 |

# 6. Next Meeting

- Date: 14th September 2026

- Time: 3:00 PM

- Venue: Seminar Hall

Prepared by: Sahil Singh

Approved by: Prof. Labhini Rahangdale